## Overview
Whole system coordination register for ENWL published May 2022
This register is published to demonstrate compliance by ENWL with the Whole System Electricity Licence condition.
It reports on compliance for licensees ENWL for the period for the period 1st April 2021 to 1st April 2022
Whole electricity system outcomes arise from actions taken between two or more parties, at least one of whom holds an electricity transmission or distribution licence, that result in both:
• An investment in the transmission and distribution electricity networks representing best value for money; and
• Improving or, at a minimum, maintaining the services and benefits received by Customers of the electricity network.
Part A | The behaviour requirements (summarised)
Clause 1 | The licensee must coordinate and cooperate with other Electricity Distributors and transmission licensees to identify actions and processes that advance the efficient and economical operation of the Total System.
Clause 2 | The licensee must consider actions proposed by Distribution System Users/Transmission System Users which seek to advance the efficient and economical operation of its network.
Clause 3 | The licensee must use all reasonable endeavours to implement actions and processes identified and proposed through coordination or user suggestions that: (a) will not negatively impact its network; and (b) are in the interest of the efficient and economical operation of the Total System.
Part B | Demonstrating compliance (summarised)
This register details completed and in progress work which demonstrates compliance with the Whole System Electricity Licence Condition.
The licensee must prepare and is required to publish on its website a coordination register demonstrating the steps it has taken to comply with Part A of this condition not later than 27 May 2022.
The licensee must keep up to date and is required to publish its coordination register (as updated) on its website at least once every 12 months from the date of initial publication.
Further information on the Whole Electricity System Licence Condition and its purpose can be found on Ofgem's website.
Decision to implement the Whole Electricity System Licence Condition D17/7A for Transmission Owners and Electricity Distributors ¦ Ofgem
Note on B19: check this date - Ofgem website says implemented 27 May 21, so add one year

## Guidance
Guidance
1 | Where a licensee is collaborating for whole system benefit but NOT with another electricity network licensee, should or can this be included within the register? e.g. if a licensee is working with any of a local / regional authority (cross-sector), transport network or gas network for whole system benefit on combined network planning, could/ should this be included? a) if no other electricity licensees included? b) if no specific proposal has come from the organisation as a ‘system user’, but this is part of effective cooperation and coordination for whole system benefit.
Yes, this can be included. It is not required by the licence which sets a floor for demonstrating compliance, but is consistent with the spirit of the licence condition, so licencees are encouraged to include.
2 | Can planned activities or actions be included in the register?
No, only once initiated. The register can also show activites and actions which are in progress, completed, abandoned and transferred into BAU.
3 | How should the 'Activities and actions' tab be completed?
The 'Activities and actions' tab of the register is structured with coordination/ cooperation activities described in columns E-P, and related actions in the following rows in columns Q-T. If you are filling in an activity, columns Q-T are blocked out and for related actions, columns E-P are blocked. Choosing a 'Type' in column A as 'Coordination and cooperation activity' or 'Related Action' will indicate which columns should be completed. As required, you can choose 'Type', copy to insert rows, or delete rows. Actions can be repeated if common to more than one activity. However, if an action is being repeated, please refer (link) to the cell instead of copy-pasting.
4 | Can the template be altered?
The template has been agreed by all electricity network licensees, working together via the Energy Networks Association. The headings/ dropdowns should not be altered, but licensees may add their own branding to the 'Overview' tab, and alter the font sizes, column widths, freeze panes and magnification in the register to display the content better.
The template will be reviewed after the first publication and two years later.
5 | Should the register refer to specific projects?
The register should describe the coordination/ cooperation activity i.e. do X. While the description may refer to projects or programmes that deliver that coordination activity, the description should not lead with the project or programme name. One project or programme may include multiple coordination and cooperation activities.

## Activities and actions
The ‘activities and actions’ tab of the register is structured with coordination/ cooperation activities described in columns E-P, and related actions in the following rows in columns Q-T. If you are filling in an activity, columns Q-T are blocked out and for related actions, columns E-P are blocked. Choosing a ‘Type’ in column A as ‘Coordination and cooperation activity’ or ‘Related Action’ will indicate which columns should be completed. As required, you can choose ‘Type’, copy to insert rows, or delete rows. Actions can be repeated if common to more than one activity. However, if an action is being repeated, please refer (link) to the cell instead of copy-pasting. |  |  |  | Relevant coordination and cooperation activities | [11 empty] | Actions or Processes arising
| Unique identifier for each row of the sheet. xxxx/00n for an activity xxxx/00n/A0m for action xxxx refers to the publishing organisation or license group; n and m refers to numbers | Lead licensee for the action or activity (not licence group) | Licensees and other stakeholders with whom collaboration was/is being carried out. | Details of the activity (could be an activity from a project or an activity that is used in multiple projects) along with its objective. Only activities that improve the economy and efficient of the whole electricity system is to be considered. Register is of activities in progress or completed, not planned. Explanation of the activity takes precedence over the project description. | In progress, Not taken forward, Complete | Latest stage / Update since the last publication / comments | When was a decision made to act upon a challenge/need. This could include the date when analysis for options was initiated. | Details of why it is relevant to whole system. | Links to reports of the project or activity | Description of any data that was shared. Include the format of the data, if applicable, and highlight any data that cannot be widely shared due to commercial sensitivity. | Links to the data not the project/activity | A brief description of the impact of the activity on the whole system, mainly along the lines of positive, neutral or negative | A brief description of the impact of the activity on the licensee, mainly along the lines of positive, neutral or negative | What is the recommended next stage? Positively, this activity would result in actions/processes that will then move on to the 'actions from coordination' sheet. If it is not taken forward, add justification. | Justification for the decision. Even if the decision is not to take things forward, a brief explanation should be added to promote learning. | Details of the action and/or process | Rough date of initiation of the action/process | New, Improving, Mature, BaU | Reference to the activity in the register that resulted in this action/process (not to be confused with internal order or project numbers)
Type | Unique ID | Licensee | Collaborating licensees and other stakeholders | Description of the coordination/ cooperation activity | Status | Latest stage /Update /comments (if any) | Coordination activity initiation date (mm/yyyy) | Whole system relevance of the activity | External links to reports on the activity (If available) | Description of data (who shared the data) [widely shared/restricted sharing] | External links for data (if available) | Impact of the activity on the whole system | Impact of the activity on licensee | Recommended next stage of the activity | Justification for recommendation | Action or Process description | Action or process initiation date (mm/yyyy) | Status | Reference of the activity or user suggestion which resulted in this action/process | Blank list | Status list | Status
Coordination and cooperation activity | ENWL/001 | All | All | Whole System Future Energy Scenarios (FES) building blocks. | Complete | This is an established business as usual process established in Open Networks Workstream 1b Product 2. | 2020-12-01 | This process considers data exchange at transmission-distribution interfaces between DSO DFES & ESO FES for agreed forecasting components, e.g. EV and heat pump volumes, electricity consumption etc. This information is used for further alignment of FES-DFES to support whole electricity system planning. | https://www.energynetworks.org/industry-hub/resource-library/open-networks-2020-ws1b-p2-coordination-of-national-and-regional-fes.pdf | Volumes of low carbon technologies including electric vehicles and heat pumps. Capacity of different types of distributed generation including wind farms, photovoltaics and gas fuelled flexible generators. Electricity consumption for domestic and non-domestic demand. All datasets per Grid Supply Point feeding area. | Links on FES and DFES can be found on ESO and DNO websites. ENWL link: https://www.enwl.co.uk/get-connected/network-information/dfes/ | Positive impact as this process allows the alignment of long-term forecasts for demand and generation used for distribution planning (DFES) and transmission planning including national system operability (ESO FES). | Positive impact as this process allows the alignment of long-term forecasts for demand and generation used for distribution planning (DFES) and transmission planning including national system operability (ESO FES). | The recommended next stage is that the agreed building blocks are reviewed and updated by all DNOs and the ESO, on an annual basis. | The annual review of building blocks allows DNOs and the ESO to tailor the data exchange to forecasting components that are relevant to both distribution network planning, transmission planning and national system operability. | [5 empty] | New | In progress
Related action | ENWL/001/A01 | All | All | [12 empty] | This is an annual whole system planning process, that informs the recalibration of forecasting scenarios used by DNOs for distribution network planning (DFES) and by the ESO for transmission planning and national system operability (FES). | 2022-12-01 | Mature | This is an annual whole system planning process that was established in Open Networks WS1b P2 (DFES-FES alignment). |  | Improving | Not taken forward
Coordination and cooperation activity | ENWL/002 | SSE | All | Simulated trials of the neutral market facilitator and whole system co-ordinator platforms as part of the overall SSE-led Transition NIC project. | In progress | Transition is currently in the close down phase, we are finalising the review of the simulated trials report and working with SSE to contribute towards the closedown report. | 2018-04-01 | Whole system co-ordination of flexible service dispatch to resolve constraints. | www.ssen-transition.com/library | Network model data in CIM format. | No links as extract from network modelling tool IPSA | If successful, this project will provide learning on approaches for the co-ordination of flexible services across voltage levels at the transmission / distribution boundary | If successful, this project will provide learning on approaches for the co-ordination of flexible services across voltage levels at the transmission / distribution boundary | At this point we are unable to recommend the next stage as we need to wait for the outcome of the current trials. | Not applicable at this stage. | [5 empty] | Mature | Complete
Coordination and cooperation activity | ENWL/003 | ENWL | N/A | Enhancement of existing voltage control relays at primary substations to provide a more granular Low Frequency Demand Disconnection (LFDD) response | In progress | Project is currently in the design phase. | 2022-03-01 | If successful, DNOs could provide a LFDD response to the ESO whilst maintaining distributed generation and other critical supplies. | https://www.enwl.co.uk/go-net-zero/innovation/smaller-projects/network-innovation-allowance/enwl027--enhanced-lfdd/ | None at present | N/A | A more granular LFDD response will minimise disruption whilst helping to protect the whole system stability. | A more granular LFDD response will minimise disruption whilst helping to protect the whole system stability. | Complete design stage and move to project trials | Trials are required to prove the concept. | [5 empty] | BaU | as BaU
Coordination and cooperation activity | ENWL/004 | ENWL | N/A | QUEST will develop and introduce a distribution network-wide, fully co-ordinated, voltage control system, with an appropriate balance between centralised and decentralised control hierarchy. | In progress | On site equipment installation has been completed as well as the he trial design. The QUEST control software has been developed and is in testing. | 2021-04-01 | The new voltage control methodology and recommended standard to be produced in QUEST could be extended to the transmission network. This project also provides greater visibility and voltage optimisation of the distribution network aiding whole system development. | https://www.enwl.co.uk/go-net-zero/innovation/key-projects/quest/ | No data has been shared so far in the project | N/A | QUEST will provide National Grid Electricity System Operator (ESO) improved visibility of real-time, embedded generation exporters and other forms of DER, and allowing “tuned” responses for demand control and OC6. | When combined with the novel application of proven technology, the QUEST software will allow DNOs to more actively manage voltage profiles across the entire network to remove voltage constraints and optimise operation. | Not defined at this time | N/A
Coordination and cooperation activity | ENWL/005 | ENWL | N/A | BiTraDER will demonstrate how access to a neutral market allows connected resources to trade their obligations bilaterally, encouraging more of them to offer flexible services, increasing availability of flexibility and thereby reducing whole system costs. | In progress | Project has successfully mobilised. With initial activity of trial scenarios completed. Customer engagement has commenced, with an positive level of customer recruitment for on going participation in the project. The high level system architecture has been developed alongside, the market structure and trading rules. | 2021-11-01 | It will improve the likelihood of customers accepting flexible connections and services, reduce barriers to the uptake of low carbon generation, introduce a new source of flexibility to the ESO, boost value for connected resources, and address concerns of capacity being neutralised by ESO contracts. | https://www.enwl.co.uk/go-net-zero/innovation/key-projects/bitrader/ | No data shared yet. | N/A | BiTraDER could be used to resolve DSO/ESO conflicts and allow flexible resources to participate in both ESO and DSO markets, potentially using the concept of obligation trading to provide resource for both ESO and DSO services. | BiTraDER could be used to resolve DSO/ESO conflicts and allow flexible resources to participate in both ESO and DSO markets, potentially using the concept of obligation trading to provide resource for both ESO and DSO services. | Project will move into design phase which will design the platform interfaces and trading rules. | Part of the NIC Project Plan.
Coordination and cooperation activity | ENWL/006 | ENWL | NGET | At South Manchester GSP, we are replacing eleven of our circuit breakers under asset replacement. NGET are also planning to replace 2 out of their 4 circuit breakers at the substation. To realise expected efficiencies, these have to be completed at the same time. As a result we are looking at the whole electricity system to ensure that the agreed solution is least cost, also meeting our environmental impact commitment of using SF6 free switchgear and addresses the flooding risk at the site. The solution we have presented as part of our final submission is to replace the switchgear with a new GIS-building designed to address the flood risk. This solution would require NGET to replace all their four circuit breakers. | In progress | We are currently in negotiations with NGET on the land agreement for the piece of land the new GIS will be built. The next stage will include signing of the User Self Build (USB), which NGET have indicated they will sign post our draft determination. As highlighted in our EJP, NGET have also indicated that our ED2 plans are not aligned with their T2 plan in that ENWL's construction programme assumes a significant delay to the planned replacement of two NGET owned 132kV circuit breakers beyond T2 and into T3. We will continue to engage with NGET on assessing the resulting network risk of the current timescales and make any necessary reasonable adjustments to our timescales. Once our project has been approved by Ofgem, NGET have advised that they will further engage with Ofgem to utilise the mechanisms in their licence to agree a deviation from their T2 plan and the significant additional investment required above what was in their T2 submission. Work Ongoing | 2020-07-01 | We are looking at the whole electricity system to ensure that the solution we agree is the total least cost for the customer, also meets our environmental impact commitment of using SF6 free switchgear and addresses the flooding risk at the site. | We have prepared and submitted an Engineering Justification Paper (EJP) and Costs Benefit Analysis (CBA) for this project. | We have shared our EJP with NGET and they have reviewed it. NGET have shared with us their high level cost estimates for the different options, which we have included in the CBA. Both NGET costs and our costs cannot be shared widely as they are commercially sensitive. | N/A | This has positive impact as it provides an integral least cost solution for both parties considering all the outage risks. | Has positive impact by removing high risk assets from the network. | Post final determination, once our project has been approved by Ofgem, NGET have advised that they will further engage with Ofgem to utilise the mechanisms in their licence to agree a deviation from their T2 plan and the significant additional investment required above what was in their T2 submission. NGET will sign the User Self Build (USB) | The decision will enable us to progress the project in a coordinated manner, thereby delivering best value for the customer
Related action | ENWL/006/A01 | ENWL | NGET | [12 empty] | Progress discussion with NGET post draft determination | 2022-07-01 | New | Signing the User Self Build (USB)
Coordination and cooperation activity | ENWL/007 | ENWL | NGET | Flooding Mitigation Works at joint/shared sites which are at risk of flooding, to be completed and costs apportioned as specified by the Engineering Technical recommendation (ETR)138. | In progress | We have carried out Flood Risk Assessment and identified sites that require intervention. Among these are shared sites with NGET and other stakeholders like generators. | 2020-05-01 | At joint or shared transmission and distribution sites at risk of flooding, mitigation works have to be carried out collaboratively, with one of the parties leading the works. The cost of the flood mitigation works will be apportioned in line with ETR138. | N/A | N/A | N/A | There will be a positive impact, as efficiencies can be realised as one party leads the mitigation works. | We expect a positive impact, as this will ensure we deliver best value to the customer. Our network will also benefit from enhanced resilience. | During the first year of RIIO-ED2 period, we will engage the concerned third parties at joint sites, scope out the work, agree cost apportionment and implement the flood mitigation works. | This ensures best outcome for the customers
Related action | ENWL/007/A01 | ENWL | NGET | [12 empty] | Progress the flood mitigation works at joint/shared Grid & Primary sites. | 2024-03-01 | Mature | We will have our flood mitigation programme, that will ensure compliance with ETR138
Coordination and cooperation activity | ENWL/008 | ENWL | NGESO | Week 24 - Providing network demand data (true demand and peak demand) and generation loading to NGESO so they can develop their transmission models accordingly (yearly action) | as BaU | N/A |  | This data exchange allows NGESO to develop their transmission models accordingly | N/A | N/A | N/A | Positive impact as it allows for continual and accurate modelling of networks. | We expect positive impact as this will ensure we deliver best value to the customer. Our network will also benefit from enhanced data accuracy. | BaU | License requirement
Coordination and cooperation activity | ENWL/009 | NGESO | ENWL | Week 42 - Providing transmission demand data (true demand and peak demand) and generation loading to ENWL so we can develop our distribution models accordingly (yearly action) | as BaU | N/A |  | This data exchange allows ENWL to develop our distribution models accordingly | N/A | N/A | N/A | Positive impact as it allows for continual and accurate modelling of networks. | We expect positive impact as this will ensure we deliver best value to the customer. Our network will also benefit from enhanced data accuracy. | BaU | License requirement
Coordination and cooperation activity | ENWL/010 | ENWL | NGESO | Week 50 - data information exchange detailing network changes that impact transmission (yearly action) | as BaU | N/A |  | This data exchange allows NGESO to develop their transmission models accordingly | N/A | N/A | N/A | Positive impact as it allows for continual and accurate modelling of networks. | We expect positive impact as this will ensure we deliver best value to the customer. Our network will also benefit from enhanced data accuracy. | BaU | License requirement
Coordination and cooperation activity | ENWL/011 | ENWL | NGESO | Appendix G updates - data information exchange that details connecting DER connections and the affected GSPs (monthly action) | as BaU | N/A |  | This data exchange allows NGESO to develop their transmission models accordingly and specify any potential upstream reinforcement. | https://www.enwl.co.uk/get-connected/network-information/heatmap-tool/ | The Appendix G data is published on our heatmap tool that allows stakeholders to view available capacity on our network. | N/A | Positive impact as it allows for continual and accurate development of our networks. It allows stakeholders to understand available headroom at the transmission boundary. | We expect positive impact as this will ensure we deliver best value to the customer. Our network will also benefit from enhanced data accuracy and it will allow stakeholders to understand available headroom at the transmission boundary. | BaU | License requirement to provide a statement of works to NGESO. This for us, is the most efficient method.
Coordination and cooperation activity | ENWL/012 | NGESO | ENWL | Regional development plan - A Regional Development Programme (RDP) is a project or study that looks at the electricity network across Great Britain. They identify areas of development between transmission and distribution networks in areas with large amounts of distributed energy resources (DERs). (Copyright NGESO) (monthly action) | as BaU | N/A |  | It can allow distribution generation access to transmission capacity ahead of reinforcement. | https://www.nationalgrideso.com/research-publications/regional-development-programmes | Summation of available capacity is found on link provided. It is specific to areas that are experiencing high transmission constraints. | N/A | Positive impact as it allows for continual and accurate development of our networks. It allows stakeholders to understand available headroom at the transmission boundary. | We expect positive impact as this will ensure we deliver best value to the customer. Our network will also benefit from enhanced data accuracy and it will allow stakeholders to understand available headroom at the transmission boundary. | BaU | Provides value add stakeholder information.
Coordination and cooperation activity | ENWL/013 | NGESO | ENWL | GC0156: Implementation of the Electricity System Restoration Standard (monthly action) | In progress | Out for Consultation |  | Restoration of demand using embedded generation on the distribution network | https://www.nationalgrideso.com/industry-information/codes/grid-code-old/modifications/gc0156-implementation-electricity-system | Overview of project | N/A | Positive impact as it allows for whole system collaborative restoration of the network. | Positive impact as it allows for whole system collaborative restoration of the network. | Work with industry to define most efficient and deliverable solution. | License / Grid Code requirement
Coordination and cooperation activity | ENWL/014 | NGESO | ENWL, NPG | Pennine Pathfinder - The ESO has identified high voltage issues in the Pennine region when the bulk GB power system is operated in low demand periods. Forecasting has identified that this is likely to be a long term issue in the region as more distributed generation is connected to the ENWL and NPG distribution networks in future, which further reduces the demand level of the transmission network seen at a grid supply point (GSP) in the region. To tackle this, Distributed Energy Resources (DERs) including those to be connected to the ENWL and NPG distribution network, which meet the minimum technical requirements specified by the NGESO, where encouraged to tender to provide a reactive power support service as this could potentially be utilised to mitigate the high voltage profile on the transmission network in the region by absorbing extra reactive power from the grid. | Complete | NGESO has completed the tendering process. ENWL undertook the technical analysis of the tendered solutions on behalf of NGESO. | 2020-08-01 | ENWL undertook the technical analysis of the tendered solutions on behalf of NGESO classing as a whole system activity. | https://www.nationalgrideso.com/future-energy/projects/pathfinders/high-voltage/Pennines | N/A | N/A | Positive impact. This was an example where a DNO undertook technical analysis of a reactive power solution to address a voltage constraint on the transmission system. This enabled NGESO to procure a service that was most cost efficient. | Positive Impact. This provided an opportunity to study a variety of proposed solutions in providing reactive power within the Pennine region. It also allowed us to work collaboratively with NGESO and NPG to provide a whole systems solution to a transmission constraint. | Closed | N/A
Coordination and cooperation activity | ENWL/015 | NGESO | ENWL | Joint transmission liaison meetings (Bi-yearly) | as BaU | N/A |  | Chance to review existing liaison and discuss whole electrical system | N/A | N/A | N/A | Positive impact as it allows for whole system collaborative data exchanges. | Positive impact as it allows for whole system collaborative data exchanges. | BaU | License requirement
Coordination and cooperation activity | ENWL/016 | NGESO | ENWL | Bi-weekly call | as BaU | Continual relationship |  | Chance to review existing liaison and discuss whole electrical system | N/A | N/A | N/A | Positive impact as it allows for whole system collaborative data exchanges. | Positive impact as it allows for whole system collaborative data exchanges. | BaU | Allows for efficient and effective planning at both distribution and transmission.
Coordination and cooperation activity | ENWL/017 | ENWL | SPEN | Yearly liaison to exchange data and discuss connections related works around our boundary GSP points (Carrington and Bold) | as BaU | Continual relationship - Recent discussions Apr 2023 |  | Exchange data and discuss connections related works around our boundary GSP points (Carrington and Bold) | N/A | N/A | N/A | Positive impact as it allows for whole system collaborative data exchanges. | Positive impact as it allows for whole system collaborative data exchanges. | BaU | Allows for efficient and effective planning at the boundary.
Coordination and cooperation activity | ENWL/018 | ENWL | SPEN | Goldborne. SPEN-ENWL Data & Information sharing Information sharing regarding large connection applications on licence area boundaries. | In progress | Initial discussions have commenced - Limited progress 22/23 | 2022-03-01 | Sharing of information and data between licensee boundary areas, on the subject of large connection requests/applications. | N/A | N/A | N/A | Positive impact on the Whole System through facilitation of improved network planning at boundary areas. | Positive impact on the Whole System through facilitation of improved network planning at boundary areas. | Continue discussions and share data and information as it becomes available. | Inform future decision making and allow for coordinated and collaborative decisions to be taken that consider the Whole System.
Coordination and cooperation activity | ENWL/019 | ENWL | SPEN, NGET | Harker Substation. Licences are exploring Whole System solutions to facilitate the increasing number of generation requests. | In progress | Work underway with collaborating licences to understand alternatives to maintain DNO system security requirements. | 2018-12-01 | Solutions are being considered that will benefit all parties and the Whole Energy System. | N/A | N/A | N/A | Intended impact is a solution that will improve network efficiency for all parties and accommodate for the increasing numbers of generation requests. | Positive impact on the Whole System through facilitation of improved network planning at boundary areas. | Consideration of joint optioneering. | Optioneering looks at solutions on a common basis across both organisations to achieve the most effective solution.
Coordination and cooperation activity | ENWL/020 | ENWL | SPEN (SPD and SPM) | P9 quarterly meeting | In progress | Early stages of development - Limited progress 22/23 | 2022-03-01 | Quarterly meeting to discuss projects, processes and initiatives which work towards whole electrical system collaboration | N/A | N/A | N/A | Positive impact as it provides a forum for whole electrical system discussions and collaborations. | Positive impact as it provides a forum for whole electrical system discussions and collaborations. | BaU | Helps to move the industry further towards whole system.
Coordination and cooperation activity | ENWL/021 | ENWL | NGED | P9 quarterly meeting | In progress | Early stages of development - Limited progress 22/23 | 2022-03-01 | Quarterly meeting to discuss projects, processes and initiatives which work towards whole electrical system collaboration | N/A | N/A | N/A | Positive impact as it provides a forum for whole electrical system discussions and collaborations. | Positive impact as it provides a forum for whole electrical system discussions and collaborations. | BaU | Helps to move the industry further towards whole system.
Coordination and cooperation activity | ENWL/022 | ENWL | NPG | P9 quarterly meeting | In progress | Early stages of development - Limited progress 22/23 | 2022-03-01 | Quarterly meeting to discuss projects, processes and initiatives which work towards whole electrical system collaboration | N/A | N/A | N/A | Positive impact as it provides a forum for whole electrical system discussions and collaborations. | Positive impact as it provides a forum for whole electrical system discussions and collaborations. | BaU | Helps to move the industry further towards whole system.
Coordination and cooperation activity | ENWL/023 | ENWL | NGESO, NPG, NGED, SPM, SPD | Agree and co-ordinate outages for across boundary work. | as BaU | Continual relationship | Ongoing | This is an opportunity to agree running and operating regimes under system abnormal conditions to maximise system security (e.g. running arrangements for a maintenance outage). | N/A | Loading data is provided by each party alongside a selection of running arrangements that would restrict the other parties work scheme. This is restricted sharing between parties. | N/A | Positive - this data sharing acts as a touch point to maximise system security and coordination under normal day-to-day operations (e.g. maintenance outages). | Positive - this data sharing acts as a touch point to maximise system security and coordination under normal day-to-day operations (e.g. maintenance outages). | Ongoing | License condition
Coordination and cooperation activity | ENWL/024 | ENWL | NGESO, NPG, NGED, SPM, SPD | Real time control and operation of the network | as BaU | Ongoing | Ongoing | Real time control and operation of the network to facilitate works on assets across boundaries. | N/A | We share data of how the network is running across boundaries, agree operational instructions and share switching programmes and loadings. This is restricted sharing between parties. | N/A | Positive interaction to maintain the security and stability of the network. This level of coordination and collaboration helps facilitate works undertaken on each network. | Positive interaction to maintain the security and stability of the network. This level of coordination and collaboration helps facilitate works undertaken on each network. | Ongoing | Operational running requirements.
Coordination and cooperation activity | ENWL/025 | ENWL | All | Network Asset Viewer (NAV) | In progress | Successfully uploaded a dataset to the NAV, awaiting IT solution for automatic refresh of data. | 2022-04-01 | Our Network Asset Viewer was developed to facilitate network planning activities for our connection customers. Our user- friendly interactive map allows the user to search by a range of criteria to identify a specific asset and explore a range of assets in an area of interest. This facilitates whole system by providing value add data to a range of customers so they can identify and design the most efficient whole electrical system. | N/A | Access is available to the NAV on an on-line viewing portal post registration, an additional registration process is required to enable download of the gpkg dataset available | https://www.enwl.co.uk/get-connected/network-information/network-asset-viewer/ | Positive - Access to entire enwl network model | Positive - external stakeholders will have access to network model information | Once the FME workbench solution being utilised is signed off, the extraction process can be automated. This will have the added benefit of increasing the regularity of data refresh. | Affords up to date network information either via the portal or by the use of the downloadable spatial dataset.
Coordination and cooperation activity | ENWL/026 | All | All | NESM - National Energy System Map. Network data from all Britain’s electricity and gas network operators will be pulled into an integrated, digital energy system map covering the entirety of Great Britain. The map will provide customers with information about energy network assets, where those assets are located as well as who owns them. | Complete | Proof of Concept (PoC) stage complete, stakeholder feedback exercise in progress. Access to the NESM is currently suspended due to heightened risk of cyber attack. |  | Making this information available will significantly improve investment decisions, support new markets like the UK’s world-leading local flexibility market, and help bring new renewable connections to the energy networks. A fully integrated, scalable and secure data sharing platform is also the first step towards developing a National Energy System Map. | https://www.energynetworks.org/newsroom/new-digital-system-map-to-harness-the-power-of-data-to-deliver-net-zero | N/A | Access to the NESM is currently suspended due to heightened risk of cyber attack. | Positive - once PoC is signed off, development of a combined national energy map allows for complete network infrastructure visibility. | Positive - Another way of getting ENWL network information out to external stakeholders. | Continue involvement with the DDSG NESM subgroup, provide data and feedback as required. | Whole system collaboration.
Coordination and cooperation activity | ENWL/027 | ENWL | All | Data Portal 1 - ENWL is on the verge of launching a new interim Data Portal. All future datasets including geospatial infrastructure footprints and network information will be available from this location on our website. This is part of a longer term data journey where it is hoped that a revised, dynamic portal will ultimately replace this version. | In progress | Short - Mid term version of the Portal is ready to be launched onto the live website - currently awaiting project progression through IT. | 2022-04-01 | Providing this level of information allows for enhanced modelling from ICPs, IDNOs and embedded generators. This will help to assess opportunities and constraints within the ENWL network. | N/A | N/A | Portal will be located within the Go-Net_Zero section of the external website https://www.enwl.co.uk/go-net-zero/ | Positive - currently all available datasets are planned to be assessed through the portal, with additional new datasets added as they become available. | Positive - Another way of getting ENWL network information out to external stakeholders. | Identify and make available further spatial and non-spatial datasets | Whole system collaboration.
Coordination and cooperation activity | ENWL/028 | ENWL | NGESO for boundary information | GSP Boundary flow information. Records of the current and power flow (active (MW) and reactive (MVAr)) into the Electricity North West Network from National Grid at Grid Supply Points (GSPs). | as BaU | Boundary flow data at our Grid Supply Points (GSP) are now available via enwl.co.uk | 2022-02-01 | Providing this level of information allows for enhanced modelling from ICPs, IDNOs and embedded generators. This will help to assess opportunities and constraints within the ENWL network. | N/A | Microsoft Excel xlsx workbook | https://www.enwl.co.uk/get-connected/network-information/gsp-boundary-flows/ | Positive - additional dataset of previously unobtainable network information | Positive - this data allows ENWL to provide value add information to customers allowing for greater transparency and whole system development. | Continually providing and refreshing dataset. | Whole system collaboration.
Coordination and cooperation activity | ENWL/029 | All | All | NUAR - National Underground Asset Register - Geospatial commission - collaborating with all stakeholders who own underground assets to map the infrastructure | In progress | New project in the proof of concept stage. Once approved the NUAR will liaise with all affected parties to obtain data sets to map the infrastructure. | 2022-05-01 | Providing this level of information will allow stakeholders to adequately plan and deliver projects taking into account the most efficient whole system solution and map impacted stakeholders from an early stage. | N/A | N/A | N/A | Will allow stakeholder a broader understanding of infrastructure impact for delivering a solution. This will also have positive safety implications as all assets will be understood helping to reduce strikes in construction. | Requirement to submit a data set at an appropriate time with refresh rates to be confirmed. | Awaiting proof of concept to be approved. | N/A
Coordination and cooperation activity | ENWL/030 | ENWL | UU | Bilateral meeting with United Utilities on Asset Management | Complete | United Utilities requested information and understanding of Asset Management within ENWL, the changing of asset life treatment, how this is being affecting price control and how asset basis is changing. | 2022-03-01 | The purpose of the meeting was to share best practice and knowledge around processes and regulation. | N/A | N/A | N/A | Sharing best practice to advance the latest understanding on asset management between industries. | Positive, best practice sharing. | United Utilities and ENWL to continue discussions on whole systems planning with a lead into whole systems resilience planning. | Best practice sharing enhances understanding.
Coordination and cooperation activity | ENWL/031 | ENWL | NGGT, NGESO, ENWL, UKPN, NGED, SGN, WWU, NGN, Cadent, SPEN SSEN, SSET | Social Value Industry Meeting | In progress | Meeting to discuss and gain consistency across networks in approach to and measurement of social value. | 2022-03-01 | To gain consistency across networks in approach to and measurement of social value. | N/A | N/A | N/A | Allows companies to develop a consistent approach in delivering an ED2 vulnerability incentive. | Positive, best practice sharing. | Working group to be developed and meet half yearly to ensure consistency in application. | Ensures best practice application.
Coordination and cooperation activity | ENWL/032 | ENWL | NGESO, NGET, NPG, NGED, SPM, SPD, UKPN, SSEN, SSET | Proposed change to the Grid Code to require an enhanced level of planning data to be exchanged at Week 24, 48, 50. This is proposed to adopt CIM method of data exchange. | In progress | Changes to the legal text of the Grid Code have been drafted. | 2020-05-01 | An enhanced level of data exchange will allow networks to better deliver their license requirement for a coordinated and efficient network. | N/A | N/A | N/A | Positive - An enhanced level of data exchange will allow networks to better deliver there license requirement for a coordinated and efficient network. | Positive - An enhanced level of data exchange will allow networks to better deliver their license requirement for a coordinated and efficient network. | Develop CIM capability to facilitate this enhanced data exchange. | CIM capability is required to exchange the significant increase in data exchange.
Coordination and cooperation activity | ENWL/033 | NGESO | All | CMP298 CUSC and CM080 STC modifications to undertake Distribution Impact Assessments. This will provide an updated Statement of Works (SoW) process helping to identify the impact of connections on one network to another. | In progress | Descion pending | 2018-04-01 | This will enable a Whole System assessment and the impact of connections through the standardisation of an 'Appendix G' aggregated assessment methodology. ENWL have applied this process across all GSPs. | https://www.nationalgrideso.com/industry-information/codes/connection-and-use-system-code-cusc-old/modifications/cmp298-updating | A link to our heatmap tool which is updated monthly that signposts capacity at each GSP. | Heatmap tool (enwl.co.uk) | Positive. This improves the Whole System coordination of connections, reducing the overall time it takes customers to hear back regarding a Statement of Works. | This will provide an improved process for completing Statement of Works | Continue with CUSC change proposal | Improved Statement of Works will support improved Whole Systems understanding.
Coordination and cooperation activity | ENWL/034 | NGESO | All | CMP328 CUSC modifications to undertake Distribution Impact Assessments (DIA) and provisions of a third party works proposal to resolve issues where a transmission connection can impact the distribution system. | In progress | Decision pending | 2019-12-11 | This will establish contractual processes, allowing for third party resolution of Whole System issues where transmission connections require a DIA. | https://www.nationalgrideso.com/industry-information/codes/connection-and-use-system-code-cusc-old/modifications/cmp328-connections | N/A | N/A | Positive. This modification proposes to put in place an appropriate process to be utilised when any transmission connection triggers a DIA. Ensuring the process in place for such connections, best reflects the necessary contractual relationship of parties involved and allows for Whole System analysis. (Copyright NGESO) | This will ensure clear contractual arrangements are in-place, facilitating whole system analysis when assessing a transmission connections impact on the distribution network (DIA). | Continue with CUSC change proposal | Having an appropriate contractual relationship in place will facilitate whole system analysis and will reflect the shared responsibilities which are needed to deliver a coordinated and efficient electricity system.
Coordination and cooperation activity | ENWL/035 | NGESO | All | Whole electricity joint forum | as BaU | Ongoing | 2021-08-12 | This is a monthly activity that acts as a collaborative forum for whole electricity system initiatives such the RDPs and other Projects. | N/A | N/A | N/A | Positive. This allows for an opportunity for DNO's and the TO to input on relevant ESO initiatives. | Allows the DNO access to the latest developments on relevant ESO initiatives | Continue attendance and engagement | Allows for whole system collaboration between parties.
Coordination and cooperation activity | ENWL/036 | ENWL | NGESO, NGET, NPG, NGED, SPM, SPD, UKPN, SSEN, SSET | Strategic Connections Working Groups | In progress | Various working groups set up to develop strategies to facilitate DER connections to the network | 2023-02-01 | To meet Net Zero targets critical to ensure DER connections are made to the Electricity Network across the country. This working group will help to enable this. | N/A | N/A | N/A | Positive - allows for all DNOs to have a co-ordinated approach to the challenges facing the industry in this area at present. | This will ensure that ENWL can align with industry best practice on this issues and act accordingly. | Continue attendance and engagement | Ensures ENWL are aware off and carrying out best practice in this area.
Coordination and cooperation activity | ENWL/037 | ENWL | NGET | ENW / NGET Regional Strategy Meeting | In progress | Two session held to provide stakeholder input into NGETs forward investment plans. | 2023-04-01 | ENW to feed into and help shape the regional requirements of NGET. | N/A | N/A | N/A | Positive allows for ENWL to provide influence on NGET plans and target investment efficiently. | Positive, best practice sharing. | Continue attendance and engagement | Allows for whole system collaboration between parties.
Coordination and cooperation activity | ENWL/038 | NGESO | ENWL,NGET,NGESO | Heysham Whole System Planning | In progress | Strategy and coordination to ensure suitable enduring solution for Hesysham GSP is developed | 2023-03-01 | Significant stakeholder interest in DER connections in the Heysham area | N/A | N/A | N/A | Positive - Key stakeholder engagement to resolve the significant DER connection challenges in the Heysham Area. | Positive - this data allows ENWL to provide value add information to customers allowing for greater transparency and whole system development. | Continue attendance and engagement | Failure to engage could result in failure for our customers to make connections in this area.
Coordination and cooperation activity | ENWL/039 | ENWL | DESNEZ,OZEV, DFT and required Motorway service areas. | Motorway Service Area Coordination - DESNEZ OZEV and DFT | In progress | Stakeholder engagement to ensure sufficient capacity is installed at Motorway Service areas to facilitate EV charging. | 2023-05-01 | Important to engage with MSA stakeholders to ensure that the increased requirements for EV charging is factored into long term planning. | N/A | Forecasts for MSAs shared by DFT - Information sensitive | N/A | Positive - Key stakeholder engagement to move forward key demand connections at MSA across the ENW area. | Positive - this data allows ENWL to provide value add information to customers allowing for greater transparency and whole system development. | Continue attendance and engagement | Failure to engage could result in delays to key MSA customer connections.
Coordination and cooperation activity | ENWL/040 | UKPN | All | Local Area Energy Planning (LAEP) best practice guidance produced with ENA Open Networks. Report titled: | In progress | Report finalised (not published yet) | 2023-05-01 | This is an ENA Open Networks product output (LAEP Best Practice product) produced with contributions from all DNOs, gas companies and NG ESO/TO | N/A | N/A | N/A | Positive as this will support local stakeholders to improve their understanding on how their network operators can support their local Net Zero plans | Allows the DNO better communicate technical data and insights to allow local stakeholders produce well informed LAEPs | Continue attendance and engagement | Ensures best practice application.
Please insert/delete rows as required

## User suggestions
Details of all proposals received during a relevant period from system users to advance the efficient and economical operation of Electricity Distributors’ and/or transmission owners’ networks. Details of any system user proposals that have been implemented (or are being implemented) as well as a concise and clear summary of proposals not deemed to be apt for implementation, including the reason(s) for that decision.
Unique identifier for each row of the sheet (starting with xxxx/U/001 where xxxx refers to the licensee) | Licensee who is publishing register | Licensees and other stakeholders with whom collaboration was/is being carried out. | domestic customer; customer commercial; Group of domestic customers; Group of commercial customers; local authority; combined authority; other infrastructure networks; generators; aggregators etc. | Date on which the user suggestion was received | Details of the suggestion. Only those suggestions that improve the economy and efficiency of the whole system is to be considered, suggestions benefitting just one user is not to be included. | Details of the relevance to whole system | Action taken based on the suggestion. Could even be decision to not take forward. | Justification of the action resulting from the user suggestion.
Unique id | Licensee | Collaborating licensees | User category | Suggestion submission date (mm/yyyy) | Description of the suggestion | Whole system relevance | Description of the action taken on the suggestion | Justification of the action
ENWL/U/001 | ENWL | All | Energy industry stakeholders |  | ENA Open Networks - This is a programme that brings together electricity and gas members, along with stakeholders such as local authorities as an industry first to consider how electricity and gas networks can work more efficiently. There are a number of work streams that look at areas of improvement, come up with a collobrating solution and engage on solutions to come to the best solution. | Work Stream 4 focuses on Whole System collobration to deliver benefits for consumers by realising more cost-effective network investment and operation across gas and electricity networks. The project has identified four key areas for development, one of which will continue from 2021: 1. Whole system Cost Benefit Analysis (WS CBA) tool based on stakeholder feedback and clarifying the interactions between CEM (WS1A P1) and WS CBA 2. Implementing a whole system optioneering service for Local Authorities to inform local development plans 3. Shaping Local Area Energy Planning (LAEP) by co-ordinating input from gas and electricity networks into Ofgem, BEIS and Energy Systems Catapult initiatives in the development of frameworks and tools 4. Monitoring innovation projects relevant to Whole Systems, from across the industry to collate and disseminate outputs and learnings | All solutions are published online with a number of stakeholder events to allow for feedback. | N/A

## Glossary
Acronym | Term
ANM | Active Network Management
API | Application Programming Interface
BEIS | Department for Business, Energy and Industrial Strategy
CBA | Cost Benefit Analysis
CIM | Common Information Model
CMP | CUSC Modification Proposal
CUSC | Connection and Use of System Code
DER | Distributed Energy Resource
DFES | Distribution Future Energy Scenarios
DIA | Distribution Impact Assessment
DNO | Distribution Network Operator
DSO | Distribution System Operator
ENA | Energy Networks Association
ENWL | Electricity North West Ltd
FES | Future Energy Scenarios
GSP | Grid Supply Point
HV | High Voltage
JSDL | Joint System Design Liaison
LAEP | Local Area Energy Planning
LFDD | Low-Frequency Demand Disconnection
LV | Low Voltage
NESM | National Energy System Map
NGESO | Electricity System Operator
NGET | National Grid Electricity Transmission
NGGT | National Grid Gas Transmission
NIA | Network Innovation Allowance
NIC | Network Innovation Competition
NPG | Northern Power Grid
NUAR | National Underground Asset Register
P9 | Product 9 - As part of ENA Open Networks
RDP | Regional Development Programme
SO | System Operator
SOW | Statement of Works
SPD | SP Distribution
SPEN | SP Energy Networks
SPM | SP Manweb
SSEN | Scottish and Southern Electricity Networks
SWOTS | South West Operational Tripping Scheme
TIA | Transmission Impact Assessment
TO | Transmission Operator
TPW | Third Party Works
UKPN | UK Power Networks
WS | Work Stream
WPD | Western Power Distribution